# Statement of Work

Global Payroll Transformation - implementation across five countries

FICTIONAL SAMPLE FOR PRODUCT DEMONSTRATION ONLY. No real parties, employees, payroll records, or legal advice.

| Reference | DEMO-SOW-2026-027 | Effective date | 15 October 2026 |
| --- | --- | --- | --- |
| Party A | Atlas Workforce B.V. | Party B | Redwood Mobility S.A. |
| Term | Implementation through 30 June 2027 | Contract value | Fixed implementation fee: EUR 240,000 |
| Governing law | The Netherlands | Document state | Draft for review |

This Statement of Work (SOW) is entered into under the fictional Master Services Agreement between Atlas Workforce B.V. and Redwood Mobility S.A. It covers the design and implementation of a standardised payroll operating model for the Netherlands, Germany, France, Spain, and Poland.

In consideration of the mutual promises in this Agreement, the parties agree as follows.

# 1. Objectives and scope

Atlas will configure country payroll workbooks, employee-data interfaces, validation controls, reporting packs, and cutover support for the five in-scope countries.

The Services include discovery, solution design, configuration, parallel payroll testing, training, go-live, and a 30-day hypercare period.

Statutory tax advice, works-council consultation, employee communications, and remediation of historic payroll errors are excluded unless added through change control.

# 2. Client dependencies

Redwood will provide complete employee master data, country calendars, collective agreement summaries, prior payroll results, and authorised decision-makers by the dates in the implementation plan.

A delay in a client dependency may move the milestone dates and result in reasonable additional fees through the change-control process.

# 3. Vendors and integrations

Atlas may coordinate with the fictional vendors CloudLedger Europe S.A., BalticPay Services sp. z o.o., and Kestrel HR Connect Ltd. Redwood remains responsible for its licences and direct vendor contracts.

No production employee data may be transferred to a vendor until the applicable security review, data processing terms, and transfer mechanism are approved.

# 4. Fees and payment

The fixed implementation fee is EUR 240,000 excluding VAT and approved travel. Invoices are payable within 30 days.

Twenty percent is invoiced on signature, 25 percent after design approval, 30 percent after completion of parallel testing, 15 percent at go-live, and 10 percent after hypercare acceptance.

# 5. Acceptance

Redwood will accept or reject each deliverable within five business days. A rejection must identify a material failure against the agreed acceptance criteria.

A deliverable is deemed accepted if Redwood does not respond within the acceptance period. Atlas will correct a valid rejection and resubmit the deliverable.

# 6. Privacy, security, and data transfers

The parties must execute a Data Processing Agreement before any production personal data is processed. Test environments must use masked or synthetic data unless the Privacy Lead approves an exception.

Support access from outside the European Economic Area requires an approved transfer impact assessment and Standard Contractual Clauses where applicable.

Atlas must notify Redwood of a confirmed personal data incident within 24 hours and provide material updates until containment.

# 7. Conditional approval

Signature and production access are conditional on Finance approval of the implementation fee, Legal approval of the MSA and this SOW, Privacy approval of the DPA and transfer approach, and completion of vendor security reviews.

# 8. Change control

Either party may request a change. Atlas will document the impact on scope, timing, resources, risks, and fees. No change is effective until a change order is signed by both parties.

# 9. Term and termination

This SOW begins on the Effective Date and continues through completion of hypercare, expected by 30 June 2027.

Either party may terminate this SOW for uncured material breach under the MSA. If Redwood terminates for convenience after design approval, it must pay fees for work performed plus 40 percent of the remaining fixed fees.

# 10. Order of precedence

The Data Processing Agreement prevails for personal-data matters, the MSA prevails for general legal terms, and this SOW prevails for scope, milestones, and fees.

# Schedule 1. Milestones and payment plan

| Milestone | Target date | Fee | Acceptance owner |
| --- | --- | --- | --- |
| Contract signature and mobilisation | 15 Oct 2026 | EUR 48,000 | Executive Sponsor |
| Solution design approved | 15 Dec 2026 | EUR 60,000 | Programme Director |
| Parallel payroll testing complete | 31 Mar 2027 | EUR 72,000 | Payroll Lead |
| Production go-live | 31 May 2027 | EUR 36,000 | Country Leads |
| Hypercare accepted | 30 Jun 2027 | EUR 24,000 | Programme Director |

# Signatures

The parties intend to be legally bound when this Agreement is signed by their authorised representatives.

| Atlas Workforce B.V. | Redwood Mobility S.A. |
| --- | --- |
| Signature: __________________________ | Signature: __________________________ |
| Name: Authorised Signatory | Name: Authorised Signatory |
| Title: ______________________________ | Title: ______________________________ |
| Date: _______________________________ | Date: _______________________________ |

End of fictional sample agreement. All entities, dates, and commercial terms are synthetic.